## Sheet1
S no. | App | Module | Submodule | Bug Description | What I understand (checked in code) | Solution (what I will do) | Status | Screenshot | Comments | Question from Claude | Your answer / suggestion (write here)
1 | admin | login |  | page is scrolling it should not (remove scroll) | [PROBABLE] AdminLogin.jsx wraps the page in min-h-screen with py-12 padding, a large logo and a p-12 card. On short or mobile viewports (100vh includes the browser address bar) the content is taller than the screen, so the page scrolls. Needs one visual check in the browser. | Use h-[100dvh] overflow-hidden on the wrapper, reduce vertical padding and card padding on short screens (py-6, p-8), shrink the logo with a height media query. No outer scroll. | Open
2 | admin, office |  |  | on loading --> showing user app skelton it should not show user app | [VERIFIED] Loader.jsx renders AppShellSkeleton (restaurant cards / category chips = the user app). It is the Suspense fallback in AdminRouter, DeliveryV2Router, Food routes, auth routes and AuthInitializer. Office uses PageLoader in app/routes.jsx, which is the same skeleton. | Create a neutral PanelLoader (logo + spinner, or a plain table skeleton for admin) and use it as the fallback for admin, office, delivery, vendor. Keep AppShellSkeleton only inside the user app. Replace PageLoader and Loader.jsx usages. | Open
3 | office | login |  | Forgot Password? is not clickable | [VERIFIED] LoginPage.jsx line ~280 is <a href="#">. There is no page, no route and no backend endpoint: officeAuth.routes.js only has send-otp, register, login. | Add /office/forgot-password page (email, OTP, new password) and two endpoints (request reset OTP, reset with OTP) reusing the OfficeOtp model and sendOfficeSignupOtpEmail. Link the button with react-router Link. Rate-limit and use generic responses (no user enumeration). | Open |  | yes | Reset by email OTP (same style as registration OTP)? Recommended: yes, email OTP + new password.
4 | office | registeration | all | Documents & Certificates --> remove autofill option | [VERIFIED] StepDocuments.jsx has handleAutoFill (lines ~103-113) that fabricates fake documents with random sizes and no url, offered through a confirm() on Next. OnboardingPage.jsx also seeds a mock email j.doe@example.com and calls startOnboardingApi with it. | Delete handleAutoFill and the confirm(); block Next until every required document is really uploaded. Remove the mock email and use the logged-in account email. Also add autoComplete="off" on text inputs if the sheet means browser autofill. Please confirm which one you meant. | Open |  | remove fake autofill feature I want autofill feature using nip number nip number should auto fill bussiness details in typable fields not image or pdf fields | Do you mean the fake 'auto-fill documents' feature, or the browser autofill on inputs? Recommended: delete the fake feature AND set autocomplete=off.
5 | office |  |  | admin not get notify (when office approval request) | [VERIFIED] No notification is created when an office completes onboarding (no notifyAdminsSafely / inbox call in the office controllers). The admin bell (useAdminNotifications.js) does not read office requests either. | On onboarding complete: create a persisted admin notification + FCM push (notifyAdminsSafely). Add an office source (office-companies?status=under_review) to the admin bell and a link to /admin/food/office-approvals. See also bug 18. | Open |  | bell,email,push | Notify admin by in-app bell only, or also email/push? Recommended: bell + push.
6 | admin | Office Onboarding Requests |  | when refresh page should redirect to same page | [VERIFIED] OfficeOnboardingRequests.jsx keeps the opened request in local state (selectedRequest). Refresh resets it, so the detail view is lost and the list shows again. | Put the id in the URL: /admin/food/office-approvals/:id (or ?id=). On mount, load that request and open the detail view. Back button then works too. | Open
7 | admin | Office Onboarding Requests |  | view --> Documents view button is not clickable | [VERIFIED] The View link is <a href={doc.url}>. Documents created by the autofill (bug 4) have no url, so the link is dead. Real uploads may also fail for PDFs if the storage URL is not public. | Remove autofill (bug 4). Render View only when doc.url exists, else a disabled 'Not available' state. Confirm the upload endpoint returns a public/raw URL for PDFs. | Open
8 | office |  |  | when admin approved office/company --> company not notified | [VERIFIED] approveOfficeCompany / rejectOfficeCompany (officeCompanyApproval.controller.js) only update the status. Nothing is sent. Reject also has no reason field. | On approve/reject send an email (existing office mailer) and an in-app record. Add a rejection reason to the reject API and show it on the company side. | Open |  | yes | Notify the company by email, in-app, or both? Recommended: email + in-app, and a rejection reason on reject.
9 | office |  |  | when admin approved office/company --> Application Under Review page should be automatically change to office dashboard | [VERIFIED] UnderReviewPage.jsx is static: no status check, no polling, no socket. Only a Back to Login button. | Poll the company status every 15-30 s and on window focus (or emit a socket event on approve). On approved redirect to /office/dashboard; on rejected show the reason. Also check status when the page loads. | Open
10 | delivery | login |  | splash screen --> showing user app skelton | [VERIFIED] Same cause as bug 2 (Loader.jsx used by DeliveryV2Router and AuthInitializer). | Fixed together with bug 2: delivery gets its own splash/loader. | Open
11 | delivery | login |  | change language --> phone no. place holder not change | [VERIFIED] config/countries.js stores raw English placeholder: "Enter 9-digit number" for every country. SignIn.jsx line ~364 passes it to the input without t(). | Build the placeholder at render time with a translated key: t("Enter {{n}}-digit number", {n: phoneLength}); add pl/ru/uk/de translations. Same fix in vendor, customer and auth/Login.jsx which share the list. Optionally localise country names with Intl.DisplayNames. | Open
12 | delivery | login |  | phone no. filed going out of box | [VERIFIED] SignIn.jsx lines ~357-382: the input is a flex child with flexGrow:1 but no minWidth:0 / width:100%; the country picker has min-w-[95px] shrink-0. Inputs have an intrinsic width, so on narrow screens the row overflows. | Add minWidth:0, width:100%, boxSizing:border-box on the input and let the row wrap/shrink. Check at 320px width. | Open |  | should be respoinsive
13 | delivery | login |  | remove vehicle type | [VERIFIED] SignIn.jsx has no vehicle type. The selector is on the Welcome screen (Welcome.jsx lines ~109-125, 252-268): Bicycle / E-bike cards with hard-coded pay rates (18-22 and 28-35 PLN/h). The selection is not used anywhere. | Remove the vehicle cards and the hard-coded earnings claims. Confirm the Welcome screen is the one meant. | Open |  | yes | Is the 'Bicycle / E-bike' card selector on the Welcome screen what you mean by login vehicle type? Recommended: remove it, including the hard-coded PLN/h rates.
14 | delivery | registeration | 1st step | remove vehicle type | [VERIFIED] SignupStep1.jsx (default 'bike', required star, lines ~53, 480-500) and SignupStep2.jsx (VEHICLES picker, handleSelectVehicle, formData.append vehicleType). Backend vehicleType is optional (zod) but the model/admin screens display it. | Remove the type field from step 1 and 2, from the payload, from the admin join-request table/filter/detail (see bug 19) and from the profile edit select. Keep vehicle name/number only if still wanted. Decision needed: remove only the type, or name and number too? | Open |  | vehicle type should only ask once in registration and in login don’t ask type in login | Remove only vehicle TYPE, or also vehicle name and number? Recommended: remove type only; keep number (needed for the driver) and make name optional.
15 | delivery | registeration | 2nd step | support is not clickable | [VERIFIED] SignupStep2.jsx header shows a help_outline icon inside a plain div (no onClick). A /food/delivery/support page already exists. | Make it a button/Link to /food/delivery/support (with aria-label) and keep the signup draft so the user can come back. | Open |  | yes
16 | delivery | registeration | 3rd step | after register should show application pending for admin approval | [VERIFIED] SignupStep2.jsx handleSubmit success only toasts 'Registration successful. Please login with OTP.' and navigates to login. The pending message exists only after a later OTP login (OTP.jsx pendingMessage). | Add a dedicated route /food/delivery/pending (status, what happens next, support link, Check status button) and navigate there right after register. Reuse the same screen for the pending-login case. | Open
17 | delivery | registeration | 3rd step | on refresh --> uploaded document should not be remove | [NEEDS REPRO] Files are meant to persist in IndexedDB (getFileFromDB) with flags in sessionStorage; blob URLs are stripped on reload. Weak points: the UI marks a document as uploaded ({file:true}) even if the IndexedDB read fails or is blocked (WebView, private mode); sessionStorage is lost when the WebView restarts; previews depend on an async load. | On mount, derive the uploaded state from what IndexedDB actually returns; if a file is missing show 'please upload again'. Move the draft details to localStorage. Add error handling/logging around IndexedDB. Needs a test on the real Android WebView. | Open |  | it is happening in app wrapper | On which device/browser does it happen (Android app WebView, Chrome)? Which documents vanish after refresh?
18 | admin |  |  | not showing all notification(approval request) | [VERIFIED] useAdminNotifications.js polls only 6 sources (restaurants, delivery joins, food approvals, 2 support types, FSSAI) every 5 minutes with Promise.all: if one call fails the whole list becomes empty. Office requests and most DailyMealBox approvals (home cooks, fleet requests, kitchen photos, agreements, ads) are not included. | Short term: Promise.allSettled + add the missing sources. Proper fix: a server-side admin inbox (a record created on every approval request, FCM + socket push, mark as read), and the bell reads that single feed. Poll every 60 s as a fallback. | Open
19 | admin | DRIVER MANAGEMENT | New Joining Request | remove job type coloum if not needed | [VERIFIED] There is no 'job type'. The column is Vehicle Type (JoinRequest.jsx lines ~382-384, 448) plus a vehicle filter (lines 33, 62) and detail rows (~813). | Remove together with bug 14. | Open
20 | delivery | home |  | header should be fixed | [VERIFIED] The welcome header card is inside DashboardHome.jsx, which scrolls with the page (main is overflow-y-auto). | Make the header sticky (top-0, z-30, solid background) or move it into NewDeliveryDashboard above the scroll area. | Open
21 | delivery |  |  | when go from home to profile --> first show in another language then show correct | [NEEDS REPRO] No single cause is provable from code. Candidates: syncAccountPreference() switches to the account's saved language after the first paint (once per login); untranslated strings (bug 22) show English; the profile data loads after render. | Apply the account language before the first render of the delivery shell (await it in AuthInitializer / splash) and avoid changing language after first paint. Need: which language is selected on the device vs the account. | Open |  | account language prefer , and most of the time it happen | Which language is selected on the device and which is saved in the driver's account? Does it happen on every Home to Profile switch or only the first?
22 | delivery | profile |  | showing almost text static | [VERIFIED] 10 driver strings used by ProfileView have no pl/ru/uk/de translation (Expired/Expires in, Loading profile, No ID uploaded, No license uploaded, No registration document, Partner Assigned, Reg:, Valid until, Verified on file), so English shows. The 'Active' badge (line ~232) and 'Zone Assigned' label (~365) are hard-coded, not tied to real data. | Add the missing translations (i18n-seed apply). Bind the badge to the real approval/online status and show the zone name from the profile. | Open
23 | restaurant | login |  | remove scroll | [VERIFIED] PhoneScreen (VendorAuthScreens.jsx line 37) uses min-h-screen with a fixed h-56 hero image and extra padding, so the content exceeds the viewport. | Flex column with h-[100dvh]; hero image gets flex-1 min-h-0 with object-cover so it shrinks instead of causing scroll. | Open
24 | restaurant | registeration |  | verify otp --> resend code is not clickable | [VERIFIED] VendorAuthScreens.jsx line ~194: <button> with no onClick and no prop for resending. | Pass onResend from App.jsx (calls requestRestaurantOtp(authPhone)), add a 30 s cooldown timer and a toast. | Open
25 | restaurant | registeration |  | verify otp --> click on continue --> showing OTP not found but, after multiple clicks its redirect to register page | [PROBABLE] OTP is single use: otp.service.js verifyOtp deletes the record on success. The Verify button has no in-flight guard, so repeated clicks send more requests that return 'OTP not found', while the first successful one navigates later. The phone is also kept only in React state (authPhone). | Disable the button and show a spinner while verifying; ignore re-entry. Persist authPhone in sessionStorage. Backend: after a successful verify return a short-lived verification token that the register call uses, instead of re-verifying the OTP. Needs one repro with network logs to confirm. | Open |  | check it your self | Does this happen on the LOGIN OTP or the REGISTER OTP? Is the network slow? A short screen recording would help.
26 | restaurant | registeration | step 2 | contact no. not showing | [VERIFIED] RegisterFormScreen gets phone={authPhone}; authPhone is plain state (App.jsx line 85, starts as ''). It is empty after a refresh or re-mount, and the disabled field shows nothing. | Persist the verified phone in sessionStorage / use restaurant_register_phone as fallback; if still empty redirect back to the phone step. | Open |  | show the nuber on the nuber firled using which it is registered but not editable
27 | restaurant | registeration | step 3 | By continuing, you agree to our Vendor Terms of Service and acknowledge your responsibilities as a licensed food provider. --> Vendor Terms of Service and acknowledge is not clickable | [VERIFIED] VendorAuthScreens.jsx line ~947: the Trans component renders <span>, not a link (the login screen correctly uses Link). | Use Link to /vendor/termsandcondition (state backTo). Because leaving the page loses the form, save the registration draft first or open the terms in a modal. | Open |  | pop up | Open the Terms in a pop-up (form stays filled) or a new page (form draft saved)? Recommended: pop-up.
28 | restaurant | profile |  | not showing phone no. | [PROBABLE] ProfileSettings shows primaryContactNumber or ownerPhone. Registration sends ownerPhone: authPhone; if authPhone was empty (bug 26) an empty phone is saved. | Fix bug 26. Backend: fall back to the phone from the OTP-verified session when the body phone is empty. Back-fill existing records with empty phone. | Open |  | show real phone of the restaurant
29 | restaurant | home |  | showing default --> today's earning | [VERIFIED] HomeDashboard.jsx line ~369 is the literal text t("337 PLN") with the label 'Updated live'. App.jsx also seeds state from mockData (INITIAL_ORDERS, INITIAL_TRANSACTIONS). | Use the earnings API (getEarnings with today's period), show loading and 0 when empty, format with money(). Start orders/transactions empty instead of mock data. | Open |  | yes restaurants commision of the delivered orders or todays subscription plans | Should 'Today's earnings' count delivered orders only, net of commission? Recommended: yes.
30 | restaurant, user, delivery |  |  | all header should be fixed | [VERIFIED] Most inner pages are already fixed/sticky. Exceptions: delivery home header (bug 20), customer HomeScreen.jsx line ~445 (relative hero header), vendor dashboard (header hidden on dashboard: App.jsx !isDashboardPage). | Add a compact sticky top bar on these three screens (title/logo + notifications) while the large hero scrolls underneath. Add scroll padding so content is not hidden. | Open |  | yes | OK to use a compact sticky top bar on the Home screens (delivery, customer, vendor) while the big header scrolls under it? Recommended: yes.
31 | restaurant | menu |  | add meal --> when enter details --> footer menu showing above the keyboard | [VERIFIED] The bottom nav is fixed bottom-0 (App.jsx line ~878). On Android WebView the viewport shrinks when the keyboard opens, so the nav is pushed up over the form. | Hide the bottom nav while an input/textarea has focus or when visualViewport.height drops below ~75% of the window. Same for delivery and customer navs. | Open
32 | admin | FOOD MANAGEMENT | Categories | create --> add background of the box | [LIKELY FIXED] The modal is bg-white inside the admin theme, where CSS forces .bg-white to var(--ad-card-bg) !important. That variable was undefined, so the box was transparent (this is the same bug fixed earlier in global.css). | Re-test after deploying the earlier global.css change. If still transparent, add an explicit inline background to this modal. | Open | https://prnt.sc/iVcf6H_y6yJ9 | already solved
33 | admin | VENDOR MANAGEMENT | Vendor Commission | minimize the length of vendor id | [VERIFIED] RestaurantCommission.jsx lines ~459-463 print the full 24-character id. | Show a short form (last 6-8 chars, 'ID ...a1b2c3') with the full id in a tooltip and a copy button; fixed column width with ellipsis. | Open |  | yes | How many characters of the vendor id should show? Recommended: last 6 + full id in tooltip and a copy button.
34 | user | welcome screen |  | logo box is tilted | [VERIFIED] OnboardingScreens.jsx lines 27 and 30 use rotate-[-2deg] (hover:rotate-0). | Remove the rotate classes. | Open
35 | user | registeration |  | all page ends button overlap footer menu | [PROBABLE] Registration steps use a fixed Continue footer (OnboardingScreens.jsx line ~269, z-[100]) while content padding is only pb-10 / pb-12 (less than the ~96 px footer) and there is no safe-area inset. The bottom nav is not shown on these routes. Needs screenshots to know which pages. | Content padding-bottom = footer height + env(safe-area-inset-bottom); or make the CTA sticky inside the page flow. Please list the affected pages. | Open |  |  | Which exact registration pages overlap? Please send a screenshot of one.
36 | user, restaurant, delivery |  |  | app is log out again & again | [VERIFIED] Client: Vendor initAuth (App.jsx ~158) wipes tokens on any getMe error, including network/5xx. axios.js: any exception in the refresh call (network, 10 s timeout) runs onRefreshFailed and clears the session. Server: access token lives only 15 min (JWT_ACCESS_EXPIRES), so refresh happens often. A changed JWT_REFRESH_SECRET after a deploy/restart would also invalidate everyone. | Clear the session only when the server says 401/invalid refresh token, never on network errors; retry with backoff. Same rule in initAuth. Extend access TTL (e.g. 1 h) or use sliding refresh. Log the reason for every forced logout. Check pm2 logs for 'Invalid refresh token' and confirm JWT secrets are fixed in the server .env. | Open |  | it should log out when manually logout only ,in all panels, no auto logout | Which app, and after roughly how many minutes does it log out? Also please share the server (pm2) log lines around a logout.
37 | restaurant | profile |  | my subscriber --> page redirect to home | [VERIFIED] Sub-views open through showSubView React state (App.jsx lines 86, 516), not through routes. Refresh or the back button leaves the overlay and lands on the dashboard. | Give each sub-view a real route (/vendor/subscribers, /vendor/profile/...) so refresh and back work. | Open
38 | restaurant | profile |  | profile module --> mobile back --> it redirect to home | [VERIFIED] Same cause as bug 37. | Fixed together with bug 37 (route-based sub-views, back returns to the previous screen). | Open
39 | restaurant |  |  | restaurant only goes to under review when document upload nd change | [VERIFIED] restaurant.service.js (~975-991): any profile update except a zone-only change sets status = 'pending'. App.jsx initAuth (lines ~106-123) then logs the vendor out and shows Under Review. | Define the list of fields that need re-approval (legal documents: licence, PAN/GST/FSSAI numbers and images, bank details). Apply all other edits immediately. Keep status approved with a 'pending update' flag and an admin 'Update request' queue, and do not log the vendor out. Please confirm the list of fields. | Open |  | yes | Which fields should still need admin re-approval? Recommended: licence/PAN/GST/FSSAI numbers + images and bank details only; everything else applies immediately.
40 | restaurant | menu |  | not showing created meal | [PROBABLE] Meals are mapped as status === 'active' ? 'Active' : 'Draft' (App.jsx ~255, 405) so pre_order and draft meals become 'Draft', and the menu/schedule sections of MenuManager.jsx (lines ~1424, 1490) list only 'Active'. The backend default status is draft. Create errors (CITY_REQUIRED, cook agreement) appear only as toasts. | Map statuses correctly (Active / Pre-order / Draft) and show all non-archived meals with a badge; refetch after create; show create errors inline. Need the exact steps/status of the missing meal. | Open |  |  | Which meal type did you create (normal or pre-order), and what message appeared? Which screen did you expect to see it on?
41 | user | plans |  | view menu --> background should not be scrollable | [VERIFIED] PlansScreen.jsx menu sheet (lines ~55-60) has no body scroll lock. | Lock body scroll while any sheet is open (shared useScrollLock hook) and add overscroll-behavior: contain to the sheet list. Apply to SubscribeSheet and other sheets. | Open
42 | user | plans |  | showing default nutritional info | [VERIFIED] The vendor app invents nutrition: App.jsx handleAddMeal uses parseInt(calories) ¦¦ 300 (protein 15, carbs 25, fats 10) with isProvided: true; MenuManager sends '300 kcal' / '15g' when empty. The customer therefore sees fake values. | Send nutrition only when entered (isProvided false otherwise) and hide it in the customer UI when not provided. Decide whether nutrition is mandatory. Clean existing meals that have exactly 300/15/25/10. | Open |  | yes | Should nutrition be mandatory for vendors, or optional and hidden for customers when empty? Recommended: optional + hidden when empty.
43 | user | plans |  | subscription plan --> showing default delivery days | [VERIFIED] SubscribeSheet.jsx: default days [1..5] and the 'Mon - Fri' / 'Every day' chip come from the plan preset (PRESET_DAYS) and ignore the vendor's real deliveryWeekdays and the weekend switches. | Default = plan preset intersected with allowedDays; label the chips from real days; disable days the vendor does not deliver. | Open
44 | user | plans |  | subscription plan --> price overview --> weekly plan --> (5days delivery) --> showing wrong (oct4 to oct11) | [VERIFIED] quote.jsx line 99 prints quote.endDate, which is exclusive (pricing.service.js line 346: endDate = start + length). So 7 days from Oct 4 shows Oct 11 (should be Oct 10); the 30-day plan in your screenshot shows Nov 3 (should be Nov 2). Also Oct 4 2026 is a Sunday, so a Mon-Fri plan has no delivery on its first day. | Show endDate minus 1 day (inclusive) or add lastDeliveryDate to the quote; display 'first delivery - last delivery'. Decide whether a weekly Mon-Fri period should start at the first delivery day. | Open |  | yes | Should a weekly Mon-Fri plan start counting at the first delivery day (not the chosen start date)? Recommended: show 'first delivery - last delivery' dates.
45 | user | plans |  | back from checkout --> it redirect to plan page instead of previous page | [VERIFIED] CustomerAppMain.jsx line ~700: onGoBack is hard-coded navigate('/user/plans') and clears selectedPlanDetails. | Use navigate(-1) with a fallback to plans when there is no history; keep the draft so the user can return. | Open
46 | user | plans |  | subscription start date --> starts from tommrow not for today | [BY DESIGN] Intentional today: SubscribeSheet.jsx default and min are tomorrow, and the server rejects earlier dates (pricing.service.js line 176 'must be tomorrow or later'). | Needs a product decision. If same-day start is wanted: server computes the earliest allowed date per slot from its order cut-off (orderCutoffHours / prep window), frontend uses that as min, checkout and quote use the same rule. Orders for today are now created immediately on activation, so vendors would see them. | Open |  | yes | Allow same-day start? If yes, use each slot's order cut-off (admin setting) to decide? Recommended: yes, cut-off based.
47 | user | plans |  |  | [NO DETAILS] The sheet has no description for this row. | Will add once you describe it. | Open |  |  | No description in the sheet. Please describe this bug.
48 | user | plans |  |  | [NO DETAILS] The sheet has no description for this row. | Will add once you describe it. | Open |  |  | No description in the sheet. Please describe this bug.
49 | user | plans |  |  | [NO DETAILS] The sheet has no description for this row. | Will add once you describe it. | Open |  |  | No description in the sheet. Please describe this bug.
50 | [6 empty] | Open

## Legend
How to use
Green headers = your original columns (S no. to Comments, same order as your sheet).
Blue headers = added by Claude: 'What I understand', 'Solution', 'Question from Claude'.
Amber header = yours: write your answer or suggestion in 'Your answer / suggestion', save, and send the file back.
The tag at the start of 'What I understand' shows how sure I am: VERIFIED (confirmed in code), PROBABLE (very likely, needs a quick check), NEEDS REPRO (cannot prove from code, need steps/device), LIKELY FIXED (already addressed earlier), BY DESIGN (works as coded, needs a decision), NO DETAILS (empty row).
Status has a drop-down (Open, In Progress, Fixed, Closed, On Hold). Everything is Open now because no code has been changed yet.
You can edit any cell, including my understanding and solution, if I got something wrong.